## Project_Data
Task ID | Activity | Start Date | End Data | Planned Cost | Actual Cost | Planned(%) | Actual% | Status | Duration(days)
1 | Site Clearing | 2026-06-01 | 2026-06-03 | 25000 | 23000 | 100 | 100 | Completed | 3
2 | Excavation | 2026-06-04 | 2026-06-08 | 60000 | 65000 | 100 | 100 | Completed | 5
3 | PCC Work | 2026-06-09 | 2026-06-11 | 40000 | 42000 | 100 | 100 | Completed | 3
4 | Footing Reinforcement | 2026-06-12 | 2026-06-15 | 75000 | 78000 | 100 | 100 | Completed | 4
5 | Footing Concrete | 2026-06-16 | 2026-06-18 | 85000 | 82000 | 100 | 100 | Completed | 3
6 | Column Starter Work | 2026-06-19 | 2026-06-21 | 50000 | 52000 | 100 | 100 | Completed | 3
7 | Plinth Beam | 2026-06-22 | 2026-06-26 | 120000 | 125000 | 100 | 100 | Completed | 5
8 | Backfilling | 2026-06-27 | 2026-06-29 | 30000 | 32000 | 100 | 100 | Completed | 3
9 | Ground Floor Columns | 2026-06-30 | 2026-07-05 | 140000 | 145000 | 100 | 100 | Completed | 6
10 | Ground Floor Slab | 2026-07-06 | 2026-07-15 | 220000 | 235000 | 100 | 100 | Completed | 10
11 | First Floor Columns | 2026-07-16 | 2026-07-20 | 150000 | 148000 | 100 | 100 | Completed | 5
12 | First Floor Slab | 2026-07-21 | 2026-07-31 | 240000 | 250000 | 100 | 100 | Completed | 11
13 | Second Floor Columns | 2026-08-01 | 2026-08-05 | 155000 | 0 | 80 | 75 | Ongoing | 5
14 | Second Floor Slab | 2026-08-06 | 2026-08-15 | 245000 | 0 | 60 | 45 | Delayed | 10
15 | Brick Masonry GF | 2026-08-16 | 2026-08-25 | 110000 | 0 | 70 | 60 | Delayed | 10
16 | Brick Masonry FF | 2026-08-26 | 2026-09-05 | 115000 | 0 | 50 | 35 | Delayed | 11
17 | Internal Plastering | 2026-09-06 | 2026-09-15 | 95000 | 0 | 30 | 20 | Ongoing | 10
18 | External Plastering | 2026-09-16 | 2026-09-25 | 105000 | 0 | 15 | 10 | Ongoing | 10
19 | Electrical Conduits | 2026-09-26 | 2026-09-30 | 80000 | 0 | 0 | 0 | Not Started | 5
20 | Plumbing Works | 2026-10-01 | 2026-10-07 | 90000 | 0 | 0 | 0 | Not Started | 7
21 | Flooring Works | 2026-10-08 | 2026-10-18 | 180000 | 0 | 0 | 0 | Not Started | 11
22 | Painting Works | 2026-10-19 | 2026-10-30 | 130000 | 0 | 0 | 0 | Not Started | 12
23 | Doors & Windows | 2026-11-01 | 2026-11-07 | 160000 | 0 | 0 | 0 | Not Started | 7
24 | Final Finishing | 2026-11-08 | 2026-11-15 | 90000 | 0 | 0 | 0 | Not Started | 8
25 | Project Handover | 2026-11-16 | 2026-11-18 | 20000 | 0 | 0 | 0 | Not Started | 3
5
100
100
Completed

## KPI
Total Budget | 2810000
Actual Cost | 1277000
Cost Variance | 1533000
Completion % | 57.8%
Delayed Tasks | 3

## Pivot_Status
Status | Count of Task ID
Completed | 12
Delayed | 3
Not Started | 7
Ongoing | 3
Grand Total | 25

## Pivot_Cost
Activity | Sum of Actual Cost | Sum of Planned Cost
Backfilling | 32000 | 30000
Brick Masonry FF | 0 | 115000
Brick Masonry GF | 0 | 110000
Column Starter Work | 52000 | 50000
Doors & Windows | 0 | 160000
Electrical Conduits | 0 | 80000
Excavation | 65000 | 60000
External Plastering | 0 | 105000
Final Finishing | 0 | 90000
First Floor Columns | 148000 | 150000
First Floor Slab | 250000 | 240000
Flooring Works | 0 | 180000
Footing Concrete | 82000 | 85000
Footing Reinforcement | 78000 | 75000
Ground Floor Columns | 145000 | 140000
Ground Floor Slab | 235000 | 220000
Internal Plastering | 0 | 95000
Painting Works | 0 | 130000
PCC Work | 42000 | 40000
Plinth Beam | 125000 | 120000
Plumbing Works | 0 | 90000
Project Handover | 0 | 20000
Second Floor Columns | 0 | 155000
Second Floor Slab | 0 | 245000
Site Clearing | 23000 | 25000
Grand Total | 1277000 | 2810000

## Dashboard
CONSTRUCTION PROJECT MANAGEMENT DASHBOARD
Total Budget | Actual cost | Cost Variance | Completion % | Delayed Tasks
2810000 | 1277000 | 1533000 | 57.8% | 3
Prepared By: Nittala Sri Divya Harshini Tool Used : Microsoft Excel